## Budget
| Qty | Cost per Unit | Comments | Link
ROSMASTER X3 ROS Robot with Mecanum Wheel for Jetson NANO 4GB | 1 | 949 | Version: Standard-NANO 4GB SUB | https://category.yahboom.net/collections/featured/products/rosmaster-x3?variant=39664834510932
Map | 1 | 100
Miscellaneous |  | 50
| Total: | 1099 | (estimated)

## Schedule
APRIL
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task 1 - Building the model
Task 2 - Implement ROSMASTER libraries and testing lane detection
Task 3 - Creating contours by using OpenCV for white broken lanes
Task 4 - Installing the stack on the AV
Task 5 - Testing and validating algorithms on maps

## RACI
Tasks | Archit Jain | Meet Shah | Sai Swaroop Reddy Vennapusa | Tejaswini Walunjkar | Yogesh Parnandi
Task 1 - Building the model | I | R/A | I | C | I/C
Task 2 - Implement ROSMASTER libraries and testing lane detection | R/A | C | I | I | R/A
Task 3 - Creating contours by using OpenCV for white broken lanes | R/A | R/A | C | R | R/A
Task 4 - Installing the stack on the AV | C | I | R/A | R | I/C
Task 5 - Testing and validating algorithms on maps | R | C | R | R/A | I/C